## Worksheet
Task_ID | Task_Name | Project | Assignee | Start_Date | Due_Date | Progress | Status | Priority | Budget | Actual_Cost
T001 | Requirements Gathering | Website Redesign | John Smith | 2024-01-05 | 2024-01-15 | 100 | Completed | High | 5000 | 4800
T002 | UI/UX Design | Website Redesign | Sarah Johnson | 2024-01-16 | 2024-02-05 | 100 | Completed | High | 8000 | 8200
T003 | Frontend Development | Website Redesign | Mike Chen | 2024-02-06 | 2024-03-10 | 75 | In Progress | High | 12000 | 9500
T004 | Backend Development | Website Redesign | David Lee | 2024-02-06 | 2024-03-10 | 70 | In Progress | High | 15000 | 11000
T005 | Testing & QA | Website Redesign | Emily Brown | 2024-03-11 | 2024-03-25 | 0 | Not Started | Medium | 4000 | 0
T006 | Project Planning | Mobile App Launch | John Smith | 2024-01-10 | 2024-01-20 | 100 | Completed | High | 3000 | 2900
T007 | Market Research | Mobile App Launch | Sarah Johnson | 2024-01-21 | 2024-02-10 | 100 | Completed | High | 6000 | 6500
T008 | App Design | Mobile App Launch | Mike Chen | 2024-02-11 | 2024-03-05 | 90 | In Progress | High | 10000 | 9200
T009 | iOS Development | Mobile App Launch | David Lee | 2024-03-06 | 2024-04-15 | 40 | In Progress | High | 18000 | 8000
T010 | Android Development | Mobile App Launch | Emily Brown | 2024-03-06 | 2024-04-15 | 35 | In Progress | High | 18000 | 7500
T011 | API Integration | Mobile App Launch | John Smith | 2024-04-01 | 2024-04-20 | 20 | In Progress | Medium | 8000 | 2000
T012 | Beta Testing | Mobile App Launch | Sarah Johnson | 2024-04-21 | 2024-05-05 | 0 | Not Started | Medium | 5000 | 0
T013 | Infrastructure Setup | Cloud Migration | Mike Chen | 2024-02-01 | 2024-02-15 | 100 | Completed | High | 12000 | 11500
T014 | Data Migration | Cloud Migration | David Lee | 2024-02-16 | 2024-03-15 | 60 | In Progress | High | 20000 | 13000
T015 | Security Configuration | Cloud Migration | Emily Brown | 2024-03-01 | 2024-03-20 | 50 | In Progress | High | 8000 | 4500
T016 | Performance Testing | Cloud Migration | John Smith | 2024-03-21 | 2024-04-05 | 0 | Not Started | Medium | 6000 | 0
T017 | Documentation | Cloud Migration | Sarah Johnson | 2024-04-06 | 2024-04-15 | 0 | Not Started | Low | 3000 | 0
T018 | Campaign Strategy | Marketing Campaign | Mike Chen | 2024-01-15 | 2024-01-30 | 100 | Completed | High | 4000 | 4200
T019 | Content Creation | Marketing Campaign | David Lee | 2024-02-01 | 2024-02-20 | 100 | Completed | High | 7000 | 7500
T020 | Social Media Setup | Marketing Campaign | Emily Brown | 2024-02-21 | 2024-03-05 | 100 | Completed | Medium | 3000 | 2800
T021 | Ad Campaign Launch | Marketing Campaign | John Smith | 2024-03-06 | 2024-03-31 | 80 | In Progress | High | 15000 | 12500
T022 | Analytics Setup | Marketing Campaign | Sarah Johnson | 2024-03-15 | 2024-03-25 | 90 | In Progress | Medium | 2000 | 1800
T023 | Performance Review | Marketing Campaign | Mike Chen | 2024-04-01 | 2024-04-10 | 0 | Not Started | Low | 1000 | 0
T024 | System Analysis | ERP Implementation | David Lee | 2024-02-10 | 2024-02-25 | 100 | Completed | High | 8000 | 8300
T025 | Vendor Selection | ERP Implementation | Emily Brown | 2024-02-26 | 2024-03-10 | 100 | Completed | High | 5000 | 4700
T026 | Module Configuration | ERP Implementation | John Smith | 2024-03-11 | 2024-04-20 | 45 | In Progress | High | 25000 | 12000
T027 | User Training | ERP Implementation | Sarah Johnson | 2024-04-15 | 2024-05-05 | 10 | In Progress | Medium | 6000 | 800
T028 | Go-Live Preparation | ERP Implementation | Mike Chen | 2024-05-06 | 2024-05-20 | 0 | Not Started | High | 4000 | 0
T029 | Post-Launch Support | ERP Implementation | David Lee | 2024-05-21 | 2024-06-10 | 0 | Not Started | Medium | 3000 | 0
T030 | Budget Review | Q1 Financial Audit | Emily Brown | 2024-03-01 | 2024-03-10 | 100 | Completed | High | 2000 | 1900